## Dashboard
AI-Assisted Project Delivery — Project Dashboard
CivicPay Implementation (fictionalized case study) ¦ Project Manager — Delivery & UAT Coordination
| Total Tickets |  | Open Tickets | Closed Tickets | High Priority
| 22 |  | 15 | 7 | 10
| Overdue |  | Blocked | Post-Go-Live | Change Requests
| 3 |  | 2 | 1 | 2
PROJECT HEALTH
UAT Status | In Progress
Overall Attention | Requires Attention
Primary Blocker | Payment gateway sandbox dependency
Immediate Focus | Close high-priority & overdue items
AI-GENERATED WEEKLY PROJECT SUMMARY
UAT progress is being affected by the pending payment gateway sandbox dependency. Several high-priority and overdue tickets require follow-up with development. Two change requests require validation across development and UAT. Immediate focus should be on resolving blockers, confirming development timelines, completing regression testing, and assessing release readiness.
PRIORITY ACTIONS |  |  |  |  | Status Breakdown
Action | Owner | Priority | Status |  | Status | Count
Follow up on payment gateway sandbox dependency | Client / PM | High | Open |  | Open | 15
Confirm timelines for overdue development tickets | Development / PM | High | Open |  | Closed | 7
Validate change-request impact | PM / Dev / QA | High | In Progress |  | Post-Go-Live | 1
Complete regression testing | QA / PM | Medium | Open
Review release / go-live readiness | PM / Client | High | Pending

## Project Data
Ticket ID | Category | Priority | Status | Owner | Dependency | UAT Impact | Due Status
T-001 | Bug | High | Open | Development | None | Retest required | Overdue
T-002 | Bug | High | Open | Development | Client clarification | Blocked | Overdue
T-003 | Bug | High | Open | Development | None | Retest required | On Track
T-004 | Bug | Normal | Closed | Development | None | Closed | On Track
T-005 | Change Request | High | Open | PM / Dev | Client confirmation | Required | On Track
T-006 | Bug | High | Open | Development | Payment gateway sandbox | Blocked | Overdue
T-007 | Bug | Normal | Closed | Development | None | Closed | On Track
T-008 | Bug | High | Open | Development | None | Retest required | On Track
T-009 | Change Request | Medium | Open | PM / Dev | Client confirmation | Required | On Track
T-010 | Bug | Normal | Closed | Development | None | Closed | On Track
T-011 | Bug | High | Open | Development | None | Retest required | On Track
T-012 | Bug | Normal | Open | Development | None | Required | On Track
T-013 | Bug | High | Open | Development | None | Retest required | On Track
T-014 | Bug | Normal | Closed | Development | None | Closed | On Track
T-015 | Bug | Normal | Closed | Development | None | Closed | On Track
T-016 | Bug | High | Open | Development | None | Retest required | On Track
T-017 | Bug | Normal | Open | Development | None | Required | On Track
T-018 | Bug | Normal | Closed | Development | None | Closed | On Track
T-019 | Bug | Normal | Closed | Development | None | Closed | On Track
T-020 | Bug | Normal | Open | Development | None | Required | On Track
T-021 | Post-Go-Live | Normal | Open | Development | None | Post-Go-Live | On Track
T-022 | Bug | High | Open | Development | None | Retest required | On Track

## RAID Log
ID | Type | Description | Impact | Owner | Action / Mitigation | Status
R-001 | Risk | Payment gateway sandbox availability delays end-to-end testing. | Timeline | PM | Escalated to vendor for a dedicated test window. | Open
R-002 | Risk | Municipal staff UAT participants have limited availability during tax season. | Timeline | PM | Scheduled short UAT blocks around peak hours. | Open
R-003 | Risk | Scope creep from informal client requests outside written requirements. | Scope | PM | All new asks routed through formal change request process. | Open
A-001 | Assumption | Client will provide test resident accounts with representative billing data. | Delivery | Project Team | Monitor against tracker. | Active
A-002 | Assumption | Payment gateway vendor SLAs remain stable through the engagement. | Delivery | PM | Confirm before go-live. | Active
A-003 | Assumption | Municipal staff assigned to UAT have authority to sign off on defect severity. | Scope | PM / Client | Confirm at UAT kickoff. | Active
I-001 | Issue | Autopay confirmation emails delayed under load in staging. | Quality | Development | Raised, fixed, retested. | Resolved
I-002 | Issue | Admin console report export timing out for large date ranges. | UAT | Development / PM | Track fix and retest. | In Progress
I-003 | Issue | Ambiguity in late-fee calculation rules surfaced late in requirements. | Scope | PM / Client | Resolved via clarification meeting. | Resolved
I-004 | Issue | Duplicate resident account creation possible under a specific edge case. | Quality | Development / PM | Raise, track, retest. | In Progress
D-001 | Dependency | Payment gateway vendor sandbox credentials. | UAT | External Vendor | Follow up for required asset. | Closed
D-002 | Dependency | Legacy billing data export for account matching. | Delivery | Migration Vendor | Track pending export. | Open
D-003 | Dependency | Municipal staff availability for UAT sign-off. | UAT | Client | Confirm schedule. | Open
D-004 | Dependency | SSL certificate provisioning for go-live domain. | Release | Client IT | Confirm before go-live. | Open
D-005 | Dependency | Final branding assets for resident portal. | UAT | Client Marketing | Follow up for required asset. | Open

## AI Workflows
Workflow | Input | AI Output | PM Validation | Final Action
Change Impact Analysis | Client change request | Impacted modules, risks, dependencies, regression areas | Validate business rules and assumptions with client | Final requirement / Jira / UAT cases
Meeting Assistant | Meeting notes | Decisions, actions, owners, deadlines, dependencies | Verify decisions, owners and deadlines were actually stated | Action tracker / Jira / UAT follow-ups
Risk Analysis | Requirements, dependencies, change requests | Candidate risks with rationale | Assign impact, owner and mitigation | Logged as active risk in RAID